## Backlog 11-13-2013
Task | 2013-10-31 | 2013-11-01 | 2013-11-02 | 2013-11-03 | 2013-11-04 | 2013-11-05 | 2013-11-06 | 2013-11-07 | 2013-11-08 | 2013-11-09 | 2013-11-10 | 2013-11-11 | 2013-11-12 | 2013-11-13 | 2013-11-14 | Total hrs | Work Remaining
Learning Curves
Learning JavaFX (Zach) | 2013-11-01: 2; 2013-11-04: 3 | 5
Learning JavaFX (Brian) | 2013-10-31: 3; 2013-11-01: 2; 2013-11-04: 2 | 7
Learning JDBC and SQLite (Matt) | 2013-11-05: 2; 2013-11-07: 2; 2013-11-14: 1 | 5
Learning JDBC and SQLite (Logan) | 2013-11-05: 2; 2013-11-07: 2; 2013-11-14: 1 | 5
Learning JDBC and SQLite (Brian) | 2013-10-31: 1; 2013-11-05: 2; 2013-11-07: 2; 2013-11-14: 1 | 6
Design Prototype
Manage Classes MVC(Zach) | 2013-11-05: 2; 2013-11-07: 2 | 4
Manage Assigments MVC(Zach) | 2013-11-10: 2; 2013-11-12: 2 | 4
Add Skills MVC (Zach) | 2013-11-03: 2 | 2
Enter Scores MVC (Zach) | 2013-11-13: 4 | 4
Manage Outcomes MVC (Zach) | [15 empty] | 2 | bar: 2013-10-31; 2013-11-14
Prototype Finishing Touches (Zach) | [15 empty] | 1 | bar: 2013-11-13
Database
Design Database
Update ER Diagrams(Logan) | 2013-11-06: 2 | 2
Update Class Diagrams(Logan) | 2013-11-07: 3 | 3
Create Database
Develop Integration Testing code for Query Classes(Brian)
Create Select Query Test Class (Brian) | 2013-11-06: 0.5; 2013-11-07: 1; 2013-11-10: 2; 2013-11-11: 2; 2013-11-12: 2 | 7.5
Create Update Query Test Class (Brian) | 2013-11-06: 0.5; 2013-11-07: 1; 2013-11-08: 1 | 2.5
Create Insert Query Test Class (Brian) | 2013-11-06: 0.5; 2013-11-07: 3 | 3.5
Create Delete Query Test Class (Brian) | 2013-11-06: 0.5; 2013-11-07: 1; 2013-11-10: 1 | 2.5
Export Backup Database Capability(Matt)
Create Select Query Class (Matt) | 2013-11-03: 0.5; 2013-11-04: 0.5; 2013-11-10: 2; 2013-11-12: 1; 2013-11-14: 2 | 6
Create Update Query Class (Matt) | 2013-11-03: 0.5; 2013-11-04: 0.5; 2013-11-08: 1; 2013-11-09: 2; 2013-11-11: 1 | 5
Create Insert Query Class (Matt) | 2013-11-03: 0.5; 2013-11-04: 0.5; 2013-11-07: 2 | 3
Create Insert Query Class (Logan) | 2013-11-07: 2.5; 2013-11-09: 2 | 4.5
Create Delete Query Class (Logan) | 2013-11-03: 0.5; 2013-11-04: 0.5; 2013-11-12: 2; 2013-11-13: 2 | 5
Create Database Façade Class (Logan) | [15 empty] | 2 | bar: 2013-11-03; 2013-11-08
Create Abstract Query Class (Logan) | 2013-11-03: 1; 2013-11-07: 0.5 | 1.5
Not planned!!!!!
Redesign Database: Add Auto Increment (Matt) | [15 empty] | 1 | bar: 2013-11-05
Redesign Database: Removed Auto Increment (Matt) | [15 empty] | 1 | bar: 2013-11-07
Redesign Database: Removed the association table between the task table, and the class table (Matt) | [15 empty] | 1 | bar: 2013-11-14
Change Table relation diagram (Matt) | 2013-11-14: 1.5 | 1.5