## Backlog 11-13-2013
Task | 2014-01-16 | 2014-01-17 | 2014-01-18 | 2014-01-19 | 2014-01-20 | 2014-01-21 | 2014-01-22 | 2014-01-23 | 2014-01-24 | 2014-01-25 | 2014-01-26 | 2014-01-27 | 2014-01-28 | 2014-01-29 | 2014-01-30 | Total hrs | Work Remaining
Database
Implement new Database Changes(Matt) | 2014-01-19: 2; 2014-01-20: 1; 2014-01-21: 1
Edit the façade to reflect the new changes to the database (Matt) | 2014-01-21: 3; 2014-01-22: 1
Testing
Integration Testing For Delete Queries(Matt) | 2014-01-24: 2
Integration Testing For Insert Queries(Matt) | 2014-01-25: 4
Integration Testing For Update Queries(Matt) | 2014-01-26: 0
Login Screen Unit Testing (LoginMVC)(Brian) | 2014-01-18: 2; 2014-01-19: 2
Welcome Screen Unit Testing (WelcomeMVC)(Brian) | bar: 2014-01-23 to 2014-01-24
Adding Classes Unit Testing (CreateClassMVC)(Brian) | 2014-01-23: 1; 2014-01-24: 2
Removing Tasks from Assignment Unit Testing (EditAssignmentMVC)(Brian) | 2014-01-24: 2
Adding Skills to a Task Unit Testing (EditSkillsMVC)(Brian) | 2014-01-27: 2
Adding Assignments to Class Unit Testing (SelectClassMVC) (Brian) | 2014-01-28: 2
GUI Development
Login Screen Implementation (LoginMVC) (Brian) | 2014-01-18: 2
Welcome Screen Screen Implementation (WelcomeMVC)(Logan) | 2014-01-18: 1.5; 2014-01-21: 2.5
Manage Class - Adding Classes Implementation (CreateClassMVC) (Zach) | 2014-01-28: 2
Select Class - Adding Students to Class Implementation (SelectClassMVC) (Zach) | 2014-01-18: 3; 2014-01-19: 3
Create Class - Adding Assignments to Class Implementation (SelectClassMVC)(Zach) | 2014-01-20: 3; 2014-01-21: 3
Adding Tasks to Assignment Implementation (EditAssignmentMVC)(Zach) | 2014-01-24: 3; 2014-01-25: 3
Edit Skills - Adding Skills to a Task Implementation (EditSkillsMVC) Removing Skills from a Task Implementation (EditSkillsMVC) (Logan) | 2014-01-25: 5; 2014-01-27: 4; 2014-01-29: 4
Enter Scores (Logan)
Learning
Learning JavaFX with SceneBuilder (Logan) Removing Skills from a Task Implementation (EditSkillsMVC) + 1 hr Adding Classes Implementation (CreateClassMVC) + 2.5 | 2014-01-18: 2.5; 2014-01-21: 1
Week Totals: | 2014-01-16: Week1; 2014-01-17: Week2
Zach: | 2014-01-16: 12; 2014-01-17: 8
Brian: | 2014-01-16: 8; 2014-01-17: 7
Logan: | 2014-01-16: 7.5; 2014-01-17: 13
Matt: | 2014-01-16: 8; 2014-01-17: 6
Total: | 2014-01-16: 35.5; 2014-01-17: 34