## Backlog 11-13-2013
Task | 2014-02-04 | 2014-02-05 | 2014-02-06 | 2014-02-07 | 2014-02-08 | 2014-02-09 | 2014-02-10 | 2014-02-11 | 2014-02-12 | 2014-02-13 | 2014-02-14 | 2014-02-15 | 2014-02-16 | 2014-02-17 | 2014-02-18
Testing
Selecting Classes Unit Testing (SelectClassMVC) (Brian) | 2014-02-04: 2; 2014-02-07: 1
LearnOBA Main Testing (LearnOBA Main & MainTabMVC) (Brian) | 2014-02-05: 2; 2014-02-11: 1
Adding Skills to a Task Unit Testing (EditSkillsMVC) (Brian) | 2014-02-07: 2
Adding Tasks to Assignment Unit Testing (EditAssignmentMVC) (Brian) | 2014-02-14: 2; 2014-02-17: 1
Removing Assignments from Classes Unit Testing (SelectClassMVC) (Brian) | 2014-02-11: 1; 2014-02-16: 2
Integration Testing (Brian) | 2014-02-11: 2; 2014-02-18: 2
Code
Selecting Classes Implementation (SelectClassMVC) (Zach) | 2014-02-05: 2; 2014-02-08: 2
Deleting Students from Class Implementation (SelectClassMVC) (Zach) | 2014-02-08: 2; 2014-02-10: 2
Adding Assignments to Class Implementation (SelectClassMVC) (Zach) | 2014-02-11: 2
Removing Assignments from Classes Implementation (SelectClassMVC) (Zach) | 2014-02-15: 4; 2014-02-16: 2
Adding Classes Implementation (CreateClassMVC) (Zach) | 2014-02-04: 2; 2014-02-15: 2; 2014-02-16: 2
Reading In A File Of Skills (Logan) | 2014-02-06: 3; 2014-02-09: 3
Insert Skill(Logan) | 2014-02-13: 4
Update Skill (Logan) | 2014-02-15: 5
Delete Skill(Logan) | 2014-02-17: 5
Database Queries
Insert Skill(Matt) | 2014-02-04: 1; 2014-02-08: 3; 2014-02-12: 1
Adding Assignments to Class Implementation (SelectClassMVC) (Matt) | 2014-02-05: 2; 2014-02-14: 2
Adding Students to Class Implementation (SelectClassMVC) (Matt) | bar: 2014-02-10; 2014-02-16
Delete Skill(Matt) | 2014-02-04: 1; 2014-02-07: 3; 2014-02-15: 1
Removing Assignments from Classes Implementation (SelectClassMVC) (Matt) | bar: 2014-02-09; 2014-02-12
Week Totals: | 2014-02-04: Week 1; 2014-02-05: Week2
Zach: | 2014-02-04: 12; 2014-02-05: 10
Brian: | 2014-02-04: 11; 2014-02-05: 7
Logan: | 2014-02-04: 6; 2014-02-05: 14
Matt: | 2014-02-04: 12; 2014-02-05: 6
Total: | 2014-02-04: 41; 2014-02-05: 37