## Sheet1
Task | 2014-03-18 | 2014-03-19 | 2014-03-20 | 2014-03-21 | 2014-03-22 | 2014-03-23 | 2014-03-24 | 2014-03-25 | 2014-03-26 | 2014-03-27 | 2014-03-28 | 2014-03-29 | 2014-03-30 | 2014-03-31 | 2014-04-01
Selecting Classes Implementation (Zach) | 2014-03-19: 3; 2014-03-20: 1; 2014-03-30: 1
Adding Assignments to Class Implementation (Zach) | 2014-03-21: 4; 2014-03-24: 5
Removing Assignments from Classes Implementation (Zach) | 2014-03-25: 3; 2014-03-28: 3
Adding Tasks to Assignment Implementation (Zach) | 2014-03-29: 3; 2014-03-30: 3
Removing Tasks from Assignment Implementation (Zach) | 2014-03-20: 3; 2014-03-30: 1
Adding Skills to a Task Implementation (Logan) | 2014-03-24: 2; 2014-03-30: 3
Removing Skills from a Task Implementation (Logan) | 2014-03-28: 6
Adding Skills to Database on Drag and Drop Operations [Insert Skill](Logan) | 2014-03-20: 2; 2014-03-29: 4
Fix/Redo Uploading a File of Skills [Reading In A File Of Skills ] (Logan) | 2014-03-22: 5; 2014-03-23: 1
Create Outcome Model and Connect Outcomes to Database (Logan) | 2014-03-23: 4; 2014-03-25: 2
Method for Creating Reports (Brian) | 2014-03-19: 2; 2014-03-21: 5; 2014-03-24: 2
Getting application to run on Mac (Brian) | 2014-03-22: 4; 2014-03-25: 5; 2014-03-31: 4
Getting application to run on Windows (Brian) | 2014-03-22: 2
Getting application to run on Linux (Brian) | 2014-03-27: 2
Selecting Classes Implementation (Brian) | 2014-03-29: 2
Adding Classes Implementation (Brian) | bar: 2014-03-30
Method for Creating Reports (Querries)(Matt) | 2014-03-19: 2; 2014-03-21: 7; 2014-03-22: 2
Research how to Salt and Hash Password (Matt) | 2014-03-24: 6; 2014-03-25: 2
Implement Salting and Hashing Password (Matt) | 2014-03-25: 1; 2014-03-27: 5
Removing Skills from a Task Implementation (Matt) | 2014-03-28: 3; 2014-03-29: 3