## Sheet1
2013
September | 29 | Install Needed Software (Eclipse, Java, JavaFX, SQLite)
October | 1 | Project Plan Draft Complete
| 6 | Understand Java, JavaFX, and SQLite. Know how to use Eclipse. | Presentations
| 8 | Project Plan Due | Milestones and Events
| 10 | Sprint 1 Starts | Unrelated to Project
| 15 | In Person Daily Scrum Meeting
| 17 | In Person Daily Scrum Meeting
| 22 | In Person Daily Scrum Meeting
| 24 | In Person Daily Scrum Meeting
Sprint 1 Review and retrospective Meeting with Dr. Foster
| ??? | Project Specification Presentation
| ??? | Project Plan Presentation
| 31 | Status Report Due
Sprint 2 Starts
??? | ??? | Prototype/Design Presentation
November | 5 | In Person Daily Scrum Meeting
| 7 | In Person Daily Scrum Meeting
| 12 | In Person Daily Scrum Meeting
| 14 | In Person Daily Scrum Meeting
| 19 | Sprint 2 Review and retrospective Meeting with Dr. Foster
| 22 | Final Presentations
| 25-29 | Thanksgiving Break - No Classes
| 28-30 | Thanksgiving Holiday - University Closed
December | 5 | Post Mortem Due
| 7-13 | Final Exams
| 14-30 | Winter Break
2014
January | 1-12 | Winter Break
| 13 | First Day of Weekday and Evening Classes
| 14 | Meet with Dr. Foster for Project Update
| 16 | Sprint 3 Starts
| 20 | Dr. Martin Luther King, Jr. Day - University Closed
| 21 | In Person Daily Scrum Meeting
| 23 | In Person Daily Scrum Meeting
| 28 | In Person Daily Scrum Meeting
| 30 | In Person Daily Scrum Meeting
Sprint 3 Review and retrospective Meeting with Dr. Foster
February | 4 | Sprint 4 Starts
| 6 | In Person Daily Scrum Meeting
| 11 | In Person Daily Scrum Meeting
| 13 | In Person Daily Scrum Meeting
| 18 | In Person Daily Scrum Meeting
Sprint 4 Review and retrospective Meeting with Dr. Foster
| 20 | Sprint 5 Starts
| 25 | In Person Daily Scrum Meeting
| 27 | In Person Daily Scrum Meeting
March | 4 | In Person Daily Scrum Meeting
| 6 | In Person Daily Scrum Meeting
Sprint 5 Review and retrospective Meeting with Dr. Foster
| 10-14 | Spring Break
| 18 | Sprint 6 Starts
| 20 | In Person Daily Scrum Meeting
| 25 | In Person Daily Scrum Meeting
| 27 | In Person Daily Scrum Meeting
April | 1 | In Person Daily Scrum Meeting
Sprint 6 Review and retrospective Meeting with Dr. Foster
| 3 | Sprint 7 Starts
| 8 | In Person Daily Scrum Meeting
| 10 | In Person Daily Scrum Meeting
| 15 | In Person Daily Scrum Meeting
| 17 | In Person Daily Scrum Meeting
Sprint 7 Review and retrospective Meeting with Dr. Foster
| 22 | Delivery
| 25 | Post Mortem
May | 3-9 | Final Exams